## Daily
PHASE | MAY | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH
| W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Requirement Gathering & Spec. | bar: MAY W4 to JUNE W3
Requirement Gathering
Requirement Analysis | bar: JUNE W1 to JUNE W2
Scope Identification
Feasibility Study | bar: JUNE W2 to JUNE W3
System Designing
Component Diagram | bar: JUNE W3 to JUNE W4
Use Case Diagram | bar: JUNE W4 to JUNE W5
Activity Modelling | bar: JUNE W4 to JUNE W5
Project Proposal | bar: JUNE W4 to JUNE W5
ER Diagram
Database Design | bar: JULY W2 to JULY W3
UI Design | bar: JULY W3 to JULY W4
SRS
Implementation | bar: AUGUST W1 to DECEMBER W2
Intiate System Modules | bar: AUGUST W1 to SEPTEMBER W1
Semester Examination | bar: SEPTEMBER W2 to OCTOBER W3
Develop System Modules | bar: MAY W4 to SEPTEMBER W3; OCTOBER W4 to MARCH W4
Integrate System Modules | bar: NOVEMBER W3 to DECEMBER W1
Perform Intial Testing
Testing | bar: DECEMBER W2 to JANUARY W4
Unit Testing | bar: MAY W4 to DECEMBER W5; MARCH W1 to MARCH W4
Integrated Testing | bar: DECEMBER W4 to JANUARY W1
System Testing | bar: MAY W4 to DECEMBER W4; JANUARY W1 to FEBRUARY W1
Acceptance Testing | bar: JANUARY W2 to JANUARY W4
Maintenance | bar: FEBRUARY W1 to MARCH W4
Setup Databases | bar: FEBRUARY W1 to FEBRUARY W3
Maintenance | bar: FEBRUARY W3 to MARCH W4
Project Schedule
Sportizza