## Daily
STAGE | PHASE NO. | PHASE OF WATERFALL MODEL | PROGRESS | MAY | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH
|  |  |  | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Set number in cell B2 to 1 for Sunday as the first day of the week; 2 for Monday. Sunday for Hebrew, US English, Canadian English
Requirement Analysis | 1.1 | Scope Identification
| 1.2 | Requirement Gathering | bar: MAY W4 to JUNE W1
| 1.3 | Requirement Analysis
| 1.4 | Feasibility Study | bar: JUNE W3
| 1.5 | UML Diagrams (Use Case, Activity, Component, Class, ER diagram & Mapping)
| 1.6 | Project Proposal & Documentation | bar: JULY W1
System Design | 2.1 | UI Design
| 2.2 | Database Design | bar: AUGUST W1 to AUGUST W2
| 2.3 | Interim Project Report and Presentation
1st Semester Examination | bar: AUGUST W4 to SEPTEMBER W4
Implementation 3.0
Testing | 4.1 | Unit Testing | bar: DECEMBER W1 to DECEMBER W2
| 4.2 | Integrated Testing
| 4.3 | System Testing | bar: JANUARY W1 to JANUARY W3
| 4.4 | Acceptance Testing
Deployment 5.0 | bar: FEBRUARY W2 to FEBRUARY W3
Maintenance 6.0
Project Schedule
Sportizza